## TestCase
Product Name |  | AliExpress.com |  | TC End Date | 18/9/2022 | TC Execution End Date | 19/09/2022 | PASS | 36
Module Name |  | User Management |  | Test Case Developed By | ISTYAK AHAMED | Browser (tested) | Yes | FAIL | 0
Developer Name (TL) |  |  |  | Test Case Reviewed By | ISTYAK AHAMED | Performance (tested) |  | Not Executed | 0
0
Test Executed by |  | ISTYAK AHAMED | [5 empty] | Out of Scope | 36
[8 empty] | TOTAL | Remarks
#SL | Module | Testing Type | Features | Sub Features | Test data | Test Case Description | Exepected Result | Actual Result | Final Status | Screen Short | Dev Comments (Not QA)
TC001 | User Management | Non Functional Testing | Register | User Interface | No data | For first time user entered the registration form | No spelling mistake or gramatical mistake | No spelling mistake or gramatical mistake | Passed
TC002 | [5 empty] | Verify if a user can see the register from clearly and can write on it | Allows user to go to the the register page | User can go | Passed
TC003 | [5 empty] | Verify all the text boxes, buttons, etc | UI should be perfect | Perfect | Passed
TC004 | [5 empty] | Verify the required fields by not filling any data | It should hide the create account button | Hide | Passed
TC005 |  | Functional Testing |  |  | No data | Verify if a user should Register by filling all the required fields properly | 1.A successful message should show. 2. Mail should send to the user | Same as expected | Passed
TC006 | [5 empty] | Verify if a user get 4 digit code in email and after veryfying it can go to the homepage | 1. Users should be registered successfully. 2. User can see the home page. | Same as expected | Passed
TC007 |  |  |  | Location search |  | Verify if user can search and select his location | User can search and select only one location | Same as expected | Passed
TC008 | [5 empty] | Verify if a user can type and select his location | User can write and select only one location |  | Passed
TC009 |  |  |  | Email address verification |  | Verify if a user can type and search email address | Can enter and search email | Same as expected | Passed
TC010 | [5 empty] | Verify if blank spaces are passed in required fields | Will not allow to blank space | Same as expected | Passed
TC011 | [5 empty] | Verify if a user can search valid email address | should show his valid email | Same as expected | Passed
TC012 |  |  |  |  | istyakgmail.com istyak@gmailcom istyak@gmail @gmail | Verify the Email text field that has an Email address without @ symbol. Verify the Email text field that has a random string instead of a real email. Verify the Email text field that has @ symbol written in words. Verify the Email text field that has a missing dot in the email address.. | It should not show the matching email | Same as expected | Passed | invalid email
TC013 | [5 empty] | Verify the Email text field takes an existing email address | Existing email message will be showen | Message showed. | Passed
TC014 |  |  |  | Password field verification | 1234 | Verify the password limit when enter value less than 6 | It should show(6-20 characters Contains numbers, letters or symbols) | Message showed. | Passed | invalid password
TC015 |  |  |  |  | 123456789089i654323456789876543234567898345678987654 | Verify the password limit when enter value greater than 20 | Not allow to type more than 20 charecters | Did not allowed | Passed
TC016 |  |  |  |  | 12345678 | Verify the password when passing only numbers | Allow to create account |  | Passed
TC017 |  |  |  |  | asdfghjk | Verify the password when passing valid data | Allow to create account | No message | Passed
TC018 | [5 empty] | Verify the password when passing only special character | Allow to create account | No message | Passed
TC019 |  |  |  | Create account | No data | Verify if a user can click create account button after filling all components | It will allow | Same as expected | Passed
TC020 | [5 empty] | Verify if a user can create account with social media sites | It will allow the user to create account | Same as expected | Passed
TC021 | [5 empty] | Verify if a user can see all the alternative ways by clicking show all segment | It will ashow the user all alternative way to register | Same as expected | Passed
TC022 |  | Non Functional Testing | Sign In | User Interface | No data | For first time user entered the Sign in form | No spelling mistake or gramatical mistake | Same as expected | Passed
TC023 | [5 empty] | Verify if user can see the sign in from clearly and can write on it | It will allows user to go to the the sign in page | Same as expected | Passed
TC024 | [5 empty] | Verify all the text boxes,buttons, etc | It will allows user to click every buttons and dropdowns | Same as expected | Passed
TC025 | [5 empty] | Verify the required fields by not filling any data | It should hide the sign in button | Hidden | Passed
TC026 | [5 empty] | Verify if blank spaces are passed in email and password fields. | 1. Go to the Site. 2. Passed blank spaces in required fields. 3. Click on the Login button | Same as expected | Passed
TC027 |  | Functional Testing |  | User Login | No data | Verify When passing a correct email and invalid password | User should not log in and should show proper error message | Same as expected | Passed
TC028 | [5 empty] | Verify when passing incorrect Email and correct password | User should not be able to log in and the error message should be displayed. | Same as expected | Passed
TC029 | [5 empty] | Verify when passing a correct username and empty password field | User should not log in and should show proper error message | Same as expected | Passed
TC030 | [5 empty] | Verify when passing correct email and password | User should log in | Yes. It was in correct format. | Passed
TC031 | [5 empty] | Verify user should get an error message when he/she enters not registered email id. | User should get an error message. | Same as expected | Passed
TC032 | [5 empty] | Verify user should get an error message when he/she enters the previous password. | User should get an error message. | Same as expected | Passed
TC033 |  |  |  | Forget Password verification |  | Verify user should get to reset when he forgets password | User should get a new window to reset | Same as expected | Passed
TC034 | [5 empty] | Verify user should able to login with a new password. | User should able to login | Same as expected | Passed
TC035 | [5 empty] | Verify Forgot Password sends a forgot password link. | User should get the forgot password link on his/her email id. | Same as expected | Passed
TC036 | [5 empty] | Verify if the user enters a new password that does not cover the basic requirements of password(6-20 characters contains numbers, letters or symbols) then the user should be displayed error message | User should get the invalid password message | Same as expected | Passed
Scope of Improvement
The password selection should be more strong

## Report
Test Case Report
| Project Name - | AliExpress.com
| Module Name - | User Module (Register and sign in) | [5 empty] | Total No. | Status
| Test Case Version | - | [5 empty] | 36 | PASS
| Written By | Istyak Ahamed | [5 empty] | 0 | FAIL
| Executed By | Istyak Ahamed | [5 empty] | 0 | Not Executed |  | New Features | Testing Scope | Testing Environment :
| Reviewed By | - | [5 empty] | 0 | Out of Scope |  |  |  | Test Environment | Google Chrome Browser
TEST EXECUTION REPORT
| Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
|  | 36 | 0 | 0 | 0 | 36
| Grand Total | 36 | 0 | 0 | 0 | 36
LIMITATIONS
| Documents |  |  |  | Received | Useful
| PRD |  |  |  | No | No
| USER STORY |  |  |  | No | No
|  | Testing Type in Scope | Description
| Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
| Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
| Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
| Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
| Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
| Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
| Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.
Project Name: AliExpress.com Sprint - 1 No. of Features:2 No. of test Cases: 36 Total Bugs: 0
Test Case Run |  | Sprint 1 |  |  |  | Compo￼nent wise
Status | Count | %
Passed | 36 | 100% |  |  |  | Total Bugs | Backend | Android | Backoffice
Blocked | 0 | 0% |  |  |  | 0 | 0 | 0 | 2
Untested | 0 | 0%
Retest | 0 | 0%
Failed | 0 | 0%
| Severity | [5 empty] | Bug-Type
Component | Critical | Major | Minor | Low | Subtotal | Component | Functional | Visual | Content | Performance | Crash | Subtotal
Backend | 0 | 0 | 0 | 0 | 0 | Backend | 0 | 0 | 0 | 0 | 0 | 0
Android | 0 | 0 | 1 | 0 | 1 | Android | 0 | 1 | 0 | 0 | 0 | 1
Backoffice | 0 | 0 | 2 | 0 | 2 | Backoffice | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 3 | 0 |  | Total | 0 | 1 | 0 | 0 | 0 | 1
|  | Component vs Severity | [5 empty] | Component vs Bug-Type
Note on B60: Specify you test run ID from TestRail here

## TestMatrix
#SN | Required Data | No | TEST MATRIX
1 | No of requirements
2 | Avg. No. of Test Cases written Per Requirements |  | Percentage of Test Cases Executed | (No. of Test Cases Executed / TotalNo. of Test Cases written) *100 | 100%
3 | Total No. of Test Cases written for all Requirements |  | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total No. of Test Cases Executed) *100 | 100%
4 | Total No. of Test Cases Executed | 36 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total No. of Test Cases Executed) *100 | 0%
5 | No. of Test Cases Passed | 36 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total No. of Test Cases Executed) *100 | 0%
6 | No. of Test Cases Failed | 0 | Percentage of Test Cases Un Executed | (No. of Test Cases Un Executed / TotalNo. of Test Cases written) *100 | 0%
7 | No. of Test Cases Blocked | 0 | Defect Density | No. of Defects found / Size(Num of requirements) | N/A
8 | Total No. of Test Cases Un Executed | 0 | Defect Removal Efficiency(DRE) | (A/A+B)*100 A =Defects identfied during testing/Fixed Defects B= Defects identfied by the customer /Missed Defects | N/A
9 | Total No. of Defects Identified | 0
10 | Critical Defects Count | 0
11 | Higher Defects Count | 0 | Defect Leakage | (No. of leakage found in UAT/No. of Defects found in Testing) * 100 | N/A
12 | Medium Defects Count | 0 | Defect Rejection Ratio | (No of Defects Rejected /Total No. of Defects Raised) * 100 | N/A
13 | Low Defects Count | 0 | Defect age | (Fixed Date-Repoted Age) | N/A
14 | Customer Defects | 0 | Customer Satisfaction | (No. of complaints per Period of time) | N/A
15 | No. of Defets found in UAT(User Acceptance Testing) | 0

## Bug Report
Bug Report
Test Case No
Issue | No issues found in this testing
Reproducing Steps
Env | CI
Module | User Management
Severity | P1
Screenshot
Responsible QA | ISTYAK AHAMED

## MindMap
AliExpress.com Mind Map